## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
StatueStudio |  | 30 DAYS | 2021-08-23 | 2021-09-22 | 2021-09-28
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-23 | 2021-08-23 | 1 DAY
1.2 | Finish webpage | 2021-08-24 | 2021-08-26 | 2 DAY
1.3 | Project Design | 2021-08-23 | 2021-08-28 | 6 DAY
2 | Coding
2.1 | Phase 1 | 2021-08-29 | 2021-09-05 | 8 DAY
2.2 | Phase 2 | 2021-09-06 | 2021-09-13 | 8 DAY
2.3 | Additional Features | 2021-09-14 | 2021-09-16 | 2 DAY
3 | Testing
3.1 | Phase 1 Testing | 2021-09-17 | 2021-09-17 | 1 DAY
3.2 | Modification /Any changes | 2021-09-18 | 2021-09-18 | 1 DAY
3.3 | Phase 2 Testing | 2021-09-19 | 2021-09-19 | 1 DAY
3.4 | Modification /Any changes | 2021-09-20 | 2021-09-20 | 1 DAY
3.5 | Final Testing | 2021-09-21 | 2021-09-21 | 1 DAY
4 | Documentation
4.1 | User Guide | 2021-09-22 | 2021-09-24 | 2 DAY
4.2 | Presentation | 2021-09-28 | 2021-09-28 | 1 DAY

## Roles & Responsiblity
Roles And Responsiblities
1 | Role | Team Leader
| Member Name | Vaibhav Ghule
| PRN No | 210543181119
| Description | Work On Frontend
2 | Role | Group Member
| Member Name | Aayushi Suryavanshi
| PRN No | 210543181001
| Description | Work On Database
3 | Role | Group Member
| Member Name | Ashish Katkar
| PRN No | 210543181038
| Description | Work On Database
4 | Role | Group Member
| Member Name | Sidharth Dixit
| PRN No | 210543181106
| Description | Work on Backend